## Project Timeline
Gantt Chart - Master's in Data Science: Anish Mahapatra
| Dec 14 - Dec 20 | Dec 21 - Dec 27 | Dec 28 - Jan 3 | Jan 4 - Jan 10 | Jan 11 - Jan 17 | Jan 18 - Jan 24 | Jan 25 - Jan 31 | Feb 1 - Feb 7 | Feb 8 - Feb 14 | Feb 15 - Feb 21 | Feb 22 - Feb 28 | Mar 1 - Mar 7 | Mar 8 - Mar 14 | Mar 15 - Mar 21 | Mar 22 - Mar 28 | Mar 29 - Apr 4 | Apr 5 - Apr 11 | Apr 12 - Apr 18 | Apr 19 - Apr 25 | Apr 26 - May 2 | May 3 - May 9 | May 10 - May 16 | May 17 - May 23
Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
Thesis Proposal Brainstorming | [9 empty] | W8 |  | W8 |  | W8 |  | W8 |  | W8 |  | W8 |  | W8
Feasibility Analysis for shortlisted ideas
Background Research and Literature Review
Research proposal draft creation
Review and iterate on request for proposal
Literature review on recent developments
Exploratory Data Analysis
Business Understanding
Data Preparation
Data Cleaning
Feature Engineering
Review and iterations for Mid - Thesis Report
Data Formatting and Integration
Model Selection
Model Iterations and Assessment
Model Evaluation
Review Model Validation Results - Phase I
Review Model Validation Results - Phase II
Work on Final Thesis
Incorporate Feedback for Final Thesis
Start Working on video presentation
Finish work on final presentation
Planned
Completed
WIP
Delayed

## Sheet1
Project Phase | Risk | Contingency Plan
Exploratory Data Analysis | Did not receive accurate data and the data is corrupted | Leverage a copy of the data stored on Google Drive for the same
Data Transformation | Jupyter Notebook on the local computer is corrupted | Use a online iPython service like Google Colab to perform the study
| Data transformation is time consuming and does not result in the format | Revisit the exploratory data analysis phase and try alternate methods
Model Building | Might not be able to implement all of the modeling techniques researched during the research space | Scale back by filtering modeling techniques prioritized on novelty and usage

## HR MVP 3.0 Timeline v1 (hidden)
HR Analytics - MVP 3.0 Gantt Chart
| 11/02 - 11/06 | 11/09 - 11/13 | 11/16 - 11/20 | 11/23 - 11/27 | 11/30 - 12/04 | 12/07 - 12/11 | 12/14 - 12/18 | 12/21 - 12/23 | 01/05 - 01/08 | 01/11 - 01/15
Activity | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |  | Block Holidays | Sprint 4
Research & Exploration | W1 | W2 | W3 | W4 (Thanksgiving) | W5 | W4 | W5 |  | W6 | W7
Research on implications of Productivity Gain in G&A workforce forecast
Research on implications of ROCCs and PMACs in workforce forecast
Ideate and discuss the approach to include aforementioned factors in workforce forecast
Conduct Workshops for AES Leadership
Discuss and finalize the agenda for workshops
Understand the implications of factors like productivity gain, ROCCs and PMACs on the workforce requirements
Receive feedback on current metrics
Finalize the list of feedback to be incorporated as per priority
Tool Refinement
Perform feasibility check on finalized feedback items
Develop necessary wireframe and obtain validation
Initiate development as per final inputs and validation on the wireframe/calculations
Review and validate development
Decommissioning for Multiple Scenarios
Perform Feasibility check on possible approaches
Discuss and finalize the approach through wireframes
Initiate development as per finalized approach
Finalize, QC and validate development
Optimization
Discuss with AES DE team for server types & additional costs
Perform trials with new server and analyze gain
Finalize server change as per gains and discussion
Update connections with the new server
Deployment and Documentation
Update documentation as per updates
Share the documents
Read out & Presentation before Energy Star Meeting
Monthly Updates of Workday Data in the tool
Operationalization*
Does not include the following | Reason
Optional: Global HRA Follow-up (Refresher)*
Tasks to be done post completion of MVP 3.0*
1. Exploration of Budget Planning/Allocation based on Median Salaries and WF Forecast
2. Operationalization via Dominos Lab
* currently not a part of MVP 3.0 as of 2nd Nov, 2020
Planned
Completed
WIP
Delayed
Dependencies

## Shortlisted Metrics - Next Step (hidden)
Metrics Shortlisted | Questions | Next Steps | ETA | Owners
No of Wind turbines | 1. Rated/Actual Generation capacity (in MW) of each turbine 2. Average/estimated number of turbines installed at overall/plant level 3. Relation between - Number of Turbines & FTE/MW & User input | 1. Discuss POV internally to incorporate this in the model 2. Initate working on formulation - Excel/Wireframe | 24/11/2020 Start on 25/11/2020 | Anish & Sparsh
PMAC/ROCC Workforce forecast & impact |  | 1. Understand & Discuss the slide shared by Americo 2. Ideate on a suitable metric/ratio to determine WF for PMAC/ROCC 3. Discuss with AES HR Team & quantify the impact (in terms of % reduction) of PMAC/ROCC workforce on Operations WF | 24/11/2020 | Shivani
Effect of "Duration Post-COD"/ "OEM Warranty Duration" on Active Operations WF |  | 1. Discuss an explanation to put forward that duration of our forecast is next 3 years & is it possible that "shift" in forecast can be visualised within these 3 years?